## Instructions
TEXAS GENERAL LAND OFFICE Community Development and Revitalization Subrecipient Monthly Activity Status Report
Subrecipients must provide monthly Activity status reporting for all sites identified in the Performance Statement (Attachment A) and relevant to the milestones therein. The Monthly Activity Status Report is due the fifth day of the month following the reporting period for the duration of the Contract. Submit the report using the Texas Integrated Grant Reporting system upload for Monthly Activity Status Reporting using the following naming convention: [SubreceipentName]-[Last4Contract#]-[FundingAllocation]_MonRpt_YYYY-mm
This report should be completed to include all activities listed in the Performance Statement (Attachment A), and should act as a cumulative narration of the pending and completed activities.
Under the Project Milestone Phase chart, each applicable milestone should be addressed.
TIGR Milestone (Pending or Complete)
Any milestone that is not applicable to the project, please enter "N/A".
Any milestone that is pending, please enter "P".
Any milestone that is complete, please enter "C-[Date Completed]"
On Schedule? (If no, describe improvement plan below.)
A brief yet descriptive for the improvement plan should be provided.
Project Summary (provide notes or information relevant to the overall contract.): Project Summary to be provided for overall update of the contract for the reporting month. Summary should include detailed description of current milestone phase and activity that is planned or has occurred for the month.
Each Performance Statement (Attachment A) activity budget should be reported. Please use the yellow shaded cell to denote the associated activity per the Attachment A. The total budget should reflect the live expenditures for other funding and budgetary information as reported in the TIGR system.
After the report has been completed, please print the "Report" tab to PDF and submit to the GLO.

## Report
GLO Community Development and Revitalization
Texas General Land Office
Subrecipient Monthly Activity Status Report
Subrecipients must provide monthly Activity status reporting for all sites identified in the Performance Statement (Attachment A) and relevant to the milestones therein.
The Monthly Activity Status Report is due the fifth day of the month following the reporting period for the duration of the Contract.
Submit the report using the Texas Integrated Grant Reporting system upload for Monthly Activity Status Reporting.
Subrecipient:
Contract Number:
Preparer Name: | [5 empty] | Contact Information:
Reporting Period (Month/ Year):
Project Title:
Project Milestone Phase |  | Att. A Budget Gates/Milestones | [5 empty] | TIGR Milestone | On Schedule? (If no, describe improvement plan below.)
(Pending or Complete)
|  | Budget Category |  | Budget Allowance
Start-Up Phase |  | PD-GA Funds |  | 0-15%
Commencement of Engineering Phase |  | Eng Funds |  | 0-30%
Commencement of Environmental Phase |  | PD-GA Funds |  | 15.01-30%
|  | PD-Env Funds |  | 0-30%
Completion of Design Phase |  | Eng Funds |  | 30.01-60%
Completion of Special Environmental Services |  | PD-Special Env Funds |  | 100%
Completion of Environmental Record Review (AUGF) |  | PD-GA Funds |  | 30.01-50%
|  | PD-Env Funds |  | 30.01-100%
Acquisition Phase (if applicable) |  | Acq Funds |  | 100%
Commencement of Bid Phase |  | PD-GA Funds |  | 50.01-60%
|  | Eng Funds |  | 60.01-70%
Commencement of Construction Phase |  | PD-GA Funds |  | 60.01-85%
|  | Eng Funds |  | 70.01-85%
|  | Construction Funds |  | 0-95%
Completion of Construction Phase |  | PD-GA Funds |  | 85.01-95%
|  | Eng Funds |  | 85.01-100%
|  | Construction Funds |  | 95.01-100%
Commencement of Planning/Study Phase |  | PD-GA Funds |  | 15.01-60%
|  | Planning Studies Funds |  | 0-85%
Completion of Planning/Study Phase |  | PD-GA Funds |  | 60.01-95%
|  | Planning Studies Funds |  | 85.01-100%
Grant Completion Report Approval |  | PD-GA Funds |  | 95.01-100%
Project Summary (provide notes or information relevant to the overall contract.):
Budget Status: | Total Grant Funds |  | Total Other Funds |  | Grant Funds Expended |  |  | Other Funds Expended | % Grant Funds Expended (Total Expended/Total Budget | % Other Funds Expended (Total Expended/Total Budget)
PD-GA Funds
PD-Env Funds
PD-Special Env Funds
Eng Funds
Acq Funds
Construction Funds
Planning Funds
Planning-GA Funds
Totals: | 0 |  |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0!

## Sheet3 (hidden)
Acquisition - buyout of residential properties
Construction/reconstruction of streets
Construction/reconstruction of water lift stations
Construction/reconstruction of water/sewer lines or systems
Rehabilitation/reconstruction of a public improvement
Rehabilitation/reconstruction of public facilities